## Issues
Issue ID | Description | Component | Responsible | Status | Comments
1 | Invalid values also accepted (Ex. : Calculates values even if "Seen" value is empty(default??)) | GUI/Backend | Bishal | Fixed | Tested
2 | Seen radio button cannot be unchecked | GUI | Bishal | Fixed | Tested
3 | Seen & "Winner" selection widgets are not visible when 'not selected' | GUI | Bishal | Fixed | Tested
4 | Even when a single 'Winner' is not selected, calculation is done (Expected behaviour : Show error "Winner not selected") | GUI/Backend | Bishal/Navaraj | Fixed | Tested
5 | It is possible to select more than one 'Winner' | GUI/Backend | Bishal/Navaraj | Fixed | Tested
6 | When 'unseen', points are still counted | Backend | Navaraj | Fixed | Tested
7 | 'Cumulative score' is hanging | Backend
8 | Empty name not handled | GUI/Backend |  | Fixed | Tested
9 | Points' box is also not visible | GUI | Bishal | Fixed | Tested
10 | Calculation is a mess, even when there is no winner selected, someone is getting money | Backend | Navaraj | Fixed | Tested
11 | When all players are selected as 'winner' and 'seen', weird error happens | Backend | Navaraj | Fixed | Tested
12 | What is the behavior if name if duplicate? |  |  | Fixed | Tested

## Features
Features to be added